|  |  |  |  |
| --- | --- | --- | --- |
| **Semester 1** | | | |
| Task name | Duration | Start | Finish |
| Project allocation | 13 days | 8/20/2022 | 9/1/2022 |
| Project Proposal and ethics form submission | 7 days | 9/2/2022 | 9/9/2022 |
| Supervisors return comments on Proposal | 7 days | 9/9/2022 | 9/16/2022 |
| Weekly updates in Weekly Status Report | 77 days | 9/16/2022 | 11/25/2022 |
| Gantt chat submission | 14 days | 9/16/2022 | 9/30/2022 |
| Progress Report submission | 42 days | 9/16/2022 | 10/28/2022 |
| Progress Presentation | 49 days | 9/16/2022 | 11/4/2022 |
| Supervisors and assessors return comments on Progress Report | 14 days | 11/4/2022 | 11/18/2022 |
| **Semester 2** | | | |
| Task name | Duration | Start | Finish |
| Weekly updates in Weekly Status Report | 91 days | 1/6/2023 | 3/31/2023 |
| Final Report draft submission | 56 days | 1/6/2023 | 3/3/2023 |
| Supervisors return comments on Final Report draft | 7 days | 3/3/2023 | 3/10/2023 |
| Poster submission | 7 days | 3/10/2023 | 3/17/2023 |
| Final Presentation, Poster session, Final Report submission | 21 days | 3/17/2023 | 4/7/2023 |